## Epic 1
User Story | Tasks | Estimate | Priority | Status
As a customer, I want to browse available travel packages, so that I can choose one that suits my | Implement search functionality for browsing travel packages | 5 days | High | In Progress
| Develop user-friendly interface to display package information | 3 days | High | In Progress
As a customer, I want to search for specific travel packages based on criteria such as destination, duration, or price range | Design and implement search feature with filtering options | 4 days | High | In Progress
| Develop sorting mechanism for search results | 2 days | Medium | In Progress
As an agent, I want to create new travel packages, specifying the included flights, hotels, and activities | Design agent interface for creating new travel packages | 4 days | High | In Progress
As an agent, I want to create new travel packages, specifying the included flights, hotels, and activities | Implement functionality to save and store created packages | 3 days | High | In Progress
As an agent, I want to modify existing travel packages, such as updating the prices, adding, or removing components, or changing package details | Develop interface for modifying existing travel packages | 5 days | Medium | In Progress
As an agent, I want to modify existing travel packages, such as updating the prices, adding, or removing components, or changing package details | Implement version control or history tracking for changes | 3 days | Medium | In Progress

## Epic 2
User Story | Task | Estimate | Priority | Status
As a customer, I want to create a booking by selecting a travel package, so that I can secure my reservation. | Implement booking process for customers selecting a travel package | 6 days | High | Planned
| Develop secure reservation system | 4 days | High | Planned
As a customer, I want to modify or cancel my booking if my plans change, ensuring flexibility. | Design and implement booking modification functionality | 4 days | Medium | Planned
As a customer, I want to modify or cancel my booking if my plans change, ensuring flexibility. | Develop cancellation process for customers | 3 days | Medium | Planned
As an agent, I want to view and manage customer bookings, including modifying or canceling them as requested. | Create interface to view and manage customer bookings | 5 days | High | Planned
As an agent, I want to view and manage customer bookings, including modifying or canceling them as requested. | Implement modification and cancellation functionality | 4 days | High | Planned
As an agent, I want to generate booking reports to track the number of bookings, revenue, and other metrics. | Design and implement booking report generation | 5 days | Medium | Planned
As an agent, I want to generate booking reports to track the number of bookings, revenue, and other metrics. | Include tracking of bookings, revenue, and other metrics | 3 days | Medium | Planned

## Epic 3
User Story | Task | Estimate | Priority | Status
As an agent, I want to create and manage agent accounts, ensuring authorized access to the system. | Design and implement agent account creation functionality | 4 days | High | Planned
| Develop agent account management system | 5 days | High | Planned
As an agent, I want to view reports on bookings and revenue, allowing me to monitor business performance. | Design reporting system for bookings and revenue | 4 days | High | Planned
| Implement reporting functionality for bookings and revenue | 3 days | High | Planned
As an agent, I want to receive notifications about new bookings, cancellations, or other relevant updates. | Set up notification system for new bookings and updates | 3 days | Medium | Planned
| Develop notification handling and delivery mechanism | 4 days | Medium | Planned
As an agent, I want to manage customer accounts, including updating personal information or handling account-related requests. | Design customer account management interface | 5 days | High | Planned
| Implement functionality for updating customer information and requests | 4 days | High | Planned

## Epic 4
User Story | Task | Estimate | Priority | Status
As a customer, I want to create a custom travel package by selecting individual components (flights, hotels, activities), allowing for personalized experiences. | Design and implement selection interface for flights, hotels, and activities | 6 days | High | Planned
| Develop functionality to store selected components for a custom package | 5 days | High | Planned
As a customer, I want to view the total cost of my custom package, including the prices of selected components and any additional fees. | Calculate and display the total cost of the custom package | 3 days | Medium | Planned
| Include any additional fees in the calculation of the total cost | 2 days | Medium | Planned
As an agent, I want to store and manage custom packages created by customers, ensuring their availability for booking. | Design database structure for storing custom packages | 4 days | High | Planned
| Implement functionality to add, update, and delete custom packages | 5 days | High | Planned

## Sheet5
User Story | Task | Estimate | Priority | Status
As a customer, I want to securely submit my payment information to complete the booking process. | Implement secure payment form for customers to submit payment information | 4 days | High | Planned
| Set up encryption and data protection measures for handling payment information | 3 days | High | Planned
As a customer, I want to receive a confirmation of my payment and booking once the transaction is successfully processed. | Develop functionality to send booking confirmation emails to customers | 2 days | Medium | Planned
As a customer, I want to receive a confirmation of my payment and booking once the transaction is successfully processed. | Include payment confirmation details in the confirmation email | 1 day | Medium | Planned
As an agent, I want to integrate a payment processing API (e.g., STRIPE) to handle customer payments securely and efficiently. | Research and select a suitable payment processing API | 2 days | High | Planned
As an agent, I want to integrate a payment processing API (e.g., STRIPE) to handle customer payments securely and efficiently. | Implement integration with the chosen payment processing API | 4 days | High | Planned

## Sheet6
User Story | Task | Estimate | Priority | Status
As a customer, I want to create a user account to access personalized features and manage my bookings. | Design and implement user account creation functionality | 3 days | High | Planned
| Develop secure user account registration process | 2 days | High | Planned
As a customer, I want to view and modify my account information, such as contact details or preferences. | Design user interface for viewing and modifying account information | 3 days | Medium | Planned
As a customer, I want to view and modify my account information, such as contact details or preferences. | Implement functionality to update account information | 2 days | Medium | Planned
As an agent, I want to manage agent accounts, including granting or revoking access privileges. | Design interface for managing agent accounts | 3 days | High | Planned
As an agent, I want to manage agent accounts, including granting or revoking access privileges. | Implement functionality to grant or revoke access privileges for agent accounts | 2 days | High | Planned
As an agent, I want to implement security measures (e.g., password hashing, authentication) to protect user accounts from unauthorized access. | Implement password hashing and storage mechanism | 3 days | High | Planned
As an agent, I want to implement security measures (e.g., password hashing, authentication) to protect user accounts from unauthorized access. | Develop authentication system for user account login | 4 days | High | Planned